## Sheet1
# | TO DO | PRIORITY | STATUS | ESTIMATED COST
1 | Inform about unit testing | 1 | In progress | 2
4 | installing necessary software | 1 | Done | 1
11 | Create prototypes for unit testing | 1 | Done | 1
5 | analize diagrams for each component | 2 | Done | 1
6 | create unit testing for components | 2 | Done-ish | 3
7 | eventual bug/incompatibility identification | 2 | to do | 3
8 | individual component testing(automatic) | 2 | to do | 2
2 | individual component testing(manual) | 3 | to do | 2
3 | component join/integration | 3 | to do | 1
9 | testing logs | 3 | to do | 1
10 | deploy | 4 | to do | 1